## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2026-03-21
Group Number |  | 35
Participant 1 |  | Dzanic Almin
Participant 2 |  | Hauser Severin
Participant 3 |  | Matuszyk Sebastian
Participant 4 |  | Strenn Maximilian
Participant 5 |  | Tykalsky Fabian
Mentor |  | Ing. Martin Docsek MSc
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Sounds research | 5 | 3 | -2
2 | Room 1 designed | 5 | 7 | 2
3 | Object research, classroom filled | 5 | 7 | 2
4 | Basic Enemy AI | 5 | 3 | -2
5 | Crouch function | 5 | 3 | -2
6 |  |  |  | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | -2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol