## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2026-05-26
Group Number |  | 35
Participant 1 |  | Dzanic Almin
Participant 2 |  | Hauser Severin
Participant 3 |  | Matuszyk Sebastian
Participant 4 |  | Strenn Maximilian
Participant 5 |  | Tykalsky Fabian
Mentor |  | Ing. Martin Docsek MSc
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
S5FT1 | Highlight Pickup Items | 1 | 2 | 1 | x |  | Es gab Probleme mit dem vorhandenen System
S5FT2 | Show Keycards in Pause Menu | 1 | 2 | 1 | x |  | Schwierigkeiten mit Photoshop
S5FT3 | Remove Keycard Counter | 0.1 | 0.1 | 0 | x |  | Einfache Umsetzung
S5FT4 | Fix Crouch Spam | 1 | 2 | 1 |  | x | Es konnte keine Lösung gefunden werden
S5FT5 | Fix Sprint System | 0.1 | 0.1 | 0 | x |  | Leichte Implementation
0
0
0
0
0
0
0
0
0
0
0
0
0
0 |  |  |  | 3 | 0 | 0
|  | Liked | Learned | Lacked | Longed for
Dzanic Almin
Hauser Severin
Matuszyk Sebastian
Strenn Maximilian
Tykalsky Fabian